## Slide 1
VC PART -1
KICK OFF – MON AUGUST 15

## Slide 2
VC PART 1
MON
AUGUST 15
KICK OFF
2 WEEKS
ITERATIONS
WED
AUGUST 31
FINAL PRES

## Slide 3
Full time during 2.5 weeks
8 HOURS PER DAY
From AUGUST 15TH to AUGUST 31th

## Slide 4
Experience 60% of software development process
COSTING/PLANNING
IMPLEMENTATION
TEST
DEPLOYMENT
AGILE
WHAT IS MISSING ?

## Slide 5
Practice and use nearly what you learned at PNC.
TESTING
LARAVEL
NPM - COMPOSER
HTML/CSS
ERD
DB
VUE
GITHUB BOARD
AGILE
REST API
FIND THE USELESS SKILL
COMPONENTS
JAVASCRIPT

## Slide 6
ROLES & RESPONSABILITIES

## Slide 7
Project Manager
Train the week leader
Review assigned tasks and progress
Control deadlines
Support technically the team
Students Group
Development team of the virtual company
Manage their “internal organization”
SCRUM MASTER
Launch the daily meeting with his/her team member
Create the tasks on GITHUB and assign them to the team
Follow the team progress on tasks

## Slide 8
DAILY meetings with TEAM
Train the SCRUM MASTER
Review assigned tasks and progress
Control deadlines
Support technically the team
PROJECT MANAGER

## Slide 9
SCRUM MASTER
Changes every week
Everyone will be leader
Write the GitHub issues for the week
Assign the milestone, the student and monitor them every day
Communicate with PM
Plan the meeting, send a list of questions
Lead the meeting
Demonstration – Q/A - Minute meeting and work log
Follow his/her team progress

## Slide 10
Update their task on GITHUB
  Progress
  Comments
Create new tasks if needed
Code and commit their code
Communicate with the SCRFUM MASTER about their progress
TEAM MEMBERS

## Slide 11
PLANNING
ITERATION 1
THU AUGUST 15
MON AUGUST 22
DEMO TO PM
ITERATION 2
MON AUGUST 22
MON AUGUST 29
DEMO TO PM
WED AUGUST 31
JURY

## Slide 12
ITERATION 1
ITERATION 2
ITERATION- BASED PROCESS
COSTING/PLANNING
IMPLEMENTATION
TEST
DEPLOYMENT - LOCAL
COSTING/PLANNING
IMPLEMENTATION
TEST
DEPLOYMENT - LOCAL

## Slide 13
NEXT ITERATION
BUGS FROM
PREVIOUS ITERATION
FEATURES FOR
THIS ITERATION
MONDAYS = WEEKLY

## Slide 14
GITHUB ORGANISATION

## Slide 15
Your board is your main tool for your project management

## Slide 16
GITHUB
WHAT YOU NEED TO KNOW
How to create an issue
How to monitor an issue
How to link GIT commit to this issue
How to interact with customer using the issue
How to create a milestone
Assignee
Type
Milestone
How to create labels

## Slide 17
MANDATORY LABELS
Migration, controller, model, routes…
Any bug to fix
ERD , Mock up , Component diagram, routes decryption
View component and inner components
Widgets re-usable ( ex : dialogs …)
Activities related to a DEMO / DELIVERY : validation, production, demo slides

## Slide 18
MILLESTONE = the WEEK ITERATION

## Slide 19
DEMO : CREATE THE ISSUES
Issue name = [BRANCH NAME] + title
Issue shall be assign to 1 member
Issue shall have a LABEL, MILLESTONE, description

## Slide 20
REQUIRED DOCUMENTS

## Slide 21
1-REQUIRED DOCUMENTS : ERD
This document shall be put in /document folder

## Slide 22
2-REQUIRED DOCUMENTS : ROUTE
This document shall be put in /document folder

## Slide 23
3-REQUIRED DOCUMENTS : MOCK UP
This document shall be put in /document folder

## Slide 24
4-REQUIRED DOCUMENTS : COMPONENTS
This document shall be put in /document folder

## Slide 25
<app>
Students[]
// A component with a list of student as data
<app>
Students[]
// app send student to card
<parent>
Students[]
// from send the event validated to parent
Students[]
<from>
Students[]
student
PROPS
<card>
valided
EMIT
<app>
Students[]
// app provides students to anymore
Students[]
<dialog>
PROVIDE
Students[]
INJECT
Students[]
// dialog gets students from a provider
<router-view>
// Vue JS built-in component

## Slide 26
EVALUATION

## Slide 27
FINAL GRADE
Team Presentation
performance
30%
2
1
Iterations
performances
70%

## Slide 28
PROJECT MANAGER
Evaluation
FRONT separation into components , communication, UI, error prevention
BACK : ROUTES + DB MODEL + VALIDATION OF DATA
ALL Clean code
ENVIROMENT configuration of development / production
DELIVERY : deploy on AWS , tag version

## Slide 29
FINAL
PRESENTATION
25 MIN PER GROUP

## Slide 30
GROUPS & COACHES & SCRUM MASTERS

## Slide 31
SHORT VIDEO VC CONTEST
Present your team in 2 min max
Originality required !
Deadline MONDAY to submit your video to : TEACHER RADY
FUN TIME

## Slide 32
Meet with your team
Understand the documents
Understand the task for this week
Prepare the question for your PM
Meet your PM
Write the list of issues for this week ( scrum master)
Assign the issues to members
TODO TODAY